## Project Gantt
MULTIVARIATE ANALYSIS PROJECT GANTT
Grup 11. Bank-India Project |  |  |  |  | Owner | [9 empty] | Duration | [5 empty] | Starting wk |  |  |  | Finishing wk
Activity | Description | Starting date | Estimated Duration (Weeks) | Deadline | Adria C. | Alicia C. | Ji | Victor G. | Victor Geo | Status | Wk-36 | Wk-37 | Wk-38 | Wk-39 | Wk-40 | Wk-41 | Wk-42 | Wk-43 | Wk-44 | Wk-45 | Wk-46 | Wk-47 | Wk-48 | Wk-49 | Wk-50 | Wk-51 | Wk-52 | Wk-01 | Wk-02 | Wk-03
Delivery D1 |  | Wk-36 (11/09/2023) | 2 | Wk-38 (18/09/2023) | [5 empty] | Completed
Activity 1 | Group creation | Wk-36 | 1 | Wk-37 | X | X | X | X | X | Completed
Activity 2 | Data exploration | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Activity 3 | Getting the Data | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Activity 4 | Data description | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Activity 5 | Data Structure overview | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Delivery D2 |  | Wk-39 (25/09/2023) | 1 | Wk-40 (05/10/2023) | [5 empty] | Completed
Activity 6 | Group Consolidation | Wk-39 | 1 | Wk-40 | X |  |  |  |  | Completed
Activity 7 | Design of the Grantt diagram & contingency plan | Wk-39 | 1 | Wk-40 |  |  | X | X |  | Completed
Activity 8 | Creation of metadata file | Wk-39 | 1 | Wk-40 | X | X |  |  | X | Completed
Delivery D3 |  | Wk-40 (02/10/2023) | 2 | Wk-44 (31/10/2023)
Activity 9 | Project introduction | Wk-40 | 1 | Wk-40 | X | X | X | X | X | Completed
Activity 10 | Index | Wk-40 | 1 | Wk-41 |  |  | X |  | X | Completed
Activity 11 | Project Motivation | Wk-40 | 1 | Wk-41 |  |  | X |  |  | Completed
Activity 12 | Data Source presentation | Wk-40 | 1 | Wk-41 |  | X | X | X |  | Completed
Activity 13 | Description of Data structure & metadata | Wk-40 | 1 | Wk-41 |  | X |  | X | X | Completed
Activity 14 | Preprocessing Justification | Wk-40 | 1 | Wk-41 | X | X | X |  |  | Completed
Activity 15 | Data Overview with R | Wk-40 | 1 | Wk-42 |  | X |  | X | X | In process
Activity 16 | Conclusion of univariate& bivariate analysis | Wk-41 | 1 | Wk-42 |  |  |  | X |  | In process
Activity 17 | PCA | Wk-41 | 1 | Wk-42 | X | X |  |  | X | In process
Activity 18 | MCA | Wk-41 | 1 | Wk-43 |  | X |  |  |  | In process
Activity 19 | MFA | Wk-41 | 1 | Wk-43 | X |  |  |  |  | Not Started
Delivery D4 |  |  |  | Wk-03 (15/01/2024)
Activity 20 | Association Rule Mining | Wk-45 | 1 | Wk-46 |  |  | X | X |  | Not Started
Activity 21 | Report writting | Wk-45 | 1 | Wk-46 |  |  | X | X |  | Not Started
Activity 22 | Hierarchical clustering | Wk-45 | 1 | Wk-46 |  |  | X | X |  | Not Started
Activity 22B | Model Based Clustering | Wk-45 | 1 | Wk-46 |  | X |  |  | X | Not Started
Activity 23 | Profiling of Clusters | Wk-45 | 1 | Wk-46 |  | X |  | X |  | Not Started
Activity 24 | Decisions tree | Wk-45 | 1 | Wk-46 | X |  |  | X |  | Not Started
Activity 25 | Discriminant Analysis (LDA) | Wk-45 | 1 | Wk-46 | X |  | X |  |  | Not Started
Activity 26 | Discussion and Conclusion | Wk-45 | 1 | Wk-46 | X |  |  | X |  | Not Started
Activity 27 | Gantt Table | Wk-47 | 3 | Wk-50 |  | X |  |  | X | Not Started
Presentation |  |  |  | Wk-03 (16/01/2024)
Activity 1 | Submit the Documentation | Wk-02 | 1 | Wk-02 | X | X | X | X | X | Not Started
Activity 2 | Making project Presentation | Wk-51 | 2 | Wk-01 | X | X | X | X | X | Not Started
Activity 3 | Practice oral presentation | Wk-01 | 1 | Wk-02 | X | X | X | X | X | Not Started

## D3
,,

## Contingency Plan
Risk | How to Prevent | How to Manage
Team member leave | Communication. If someone is going to leave and the other members are aware of it the risk to the project is less | Readjustment of task distributions
Data Source untrustable | Ensure that the source of the database is trustable before making any further analysis | Be transparent at the report: write about what is known about the source and outline the reasons why it is not trustable
Work progress is lost | Each member will have at least one backup of all the project | Start again from a previous version
Inconsistency of versions in scripts | Use a version control platform like GitHub or a base script, where all the members start their work | Merge scripts
Communication lost with one member | We will have at least two ways to contact each of the members, like Gmail and WhatsApp | Contact the person from an alternative way
A team member is overworked | Have a good task distribution according to the workload of the semester | Readjustment of task distributions
Difficulties when applying a method (e.g., PCA) | Communication during all work giving tips and help when needed | Collaboration in the team. Other members can work in an activity initially planned for one if required
Imputation is done incorrectly (e.g., distributions before and after clearly differ) | The imputation is done by different methods and by different people | Repeat the imputation by another method, if possible, or leave missing values
Difficulties to explain any relation with the initial target variable in mining analysis (e.g., we do not manage to predict sales in the next 6 months) | Bibliography research or use of more advance mining techniques | Be transparent in the report
One member cannot attend the final presentation of the project | Members will know all the presentation | The explanation of the missing member is divided into the other members
Difficulties to explain the initial target variable in mining analysis (eg: we do not manage to predict sales in the next 6 months) | Perform several analysis | Be transparent in the report
One member cannot attend the final presentation of the project | Members will know all the presentation | The explanation of the missing member is divided into the other members