## Project Gantt
MULTIVARIATE ANALYSIS PROJECT
Grup 11. Bank-India Project |  |  |  |  | Owner | [9 empty] | Duration | [5 empty] | Starting wk |  |  |  | Finishing wk
Activity | Description | Starting date | Estimated Duration (Weeks) | Deadline | Adria C. | Alicia C. | Ji | Victor G. | Victor Geo | Status | Wk-36 | Wk-37 | Wk-38 | Wk-39 | Wk-40 | Wk-41 | Wk-42 | Wk-43 | Wk-44 | Wk-45 | Wk-46 | Wk-47 | Wk-48 | Wk-49 | Wk-50 | Wk-51 | Wk-52 | Wk-01 | Wk-02 | Wk-03
Delivery D1 |  | Wk-36 (11/09/2023) | 2 | Wk-38 (18/09/2023)
Activity 1 | Group creation | Wk-36 | 1 | Wk-37 | X | X | X | X | X | Completed
Activity 2 | Data exploration | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Activity 3 | Getting the Data | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Activity 4 | Data description | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Activity 5 | Data Structure overview | wk-37 | 1 | Wk-38 | X | X | X | X | X | Completed
Delivery D2 |  | Wk-39 (25/09/2023) | 1 | Wk-40 (05/10/2023)
Activity 6 | Group Consolidation | Wk-39 | 1 | Wk-40 | X |  |  |  |  | Completed
Activity 7 | Design of the Grantt diagram & contingency plan | Wk-39 | 1 | Wk-40 |  |  | X | X |  | In-Progress
Activity 8 | Creation of metadata file | Wk-39 | 1 | Wk-40 | X | X |  |  | X | In-Progress
Delivery D3 Part 1 |  | Wk-40 (02/10/2023) | 2 | Wk-42 (15/10/2023) TBC
Activity 9 | Task assigment | Wk-40 | 1 | Wk-40 | X | X |  |  |  | Not Started
Activity 10 | Index | Wk-40 | 1 | Wk-41 | X | X |  |  |  | Not Started
Activity 11 | Project Motivation | Wk-40 | 1 | Wk-41 | X | X |  |  |  | Not Started
Activity 12 | Data Source presentation | Wk-40 | 1 | Wk-41 |  |  |  | X | X | Not Started
Activity 13 | Description of Data structure & metadata | Wk-40 | 1 | Wk-41 |  | X | X |  |  | Not Started
Activity 14 | Decision Description | Wk-40 | 1 | Wk-41 | X | X |  |  |  | Not Started
Activity 15 | Data Overview with R | Wk-40 | 1 | Wk-41 |  |  |  | X | X | Not Started
Activity 16 | Conclusion of univariate& bivariate analysis | Wk-41 | 1 | Wk-42 |  | X | X |  |  | Not Started
Activity 17 | PCA | Wk-41 | 1 | Wk-42 |  | X | X | X |  | Not Started
Activity 18 | ACM Analysis | Wk-41 | 1 | Wk-42 | X |  |  | X | X | Not Started
Activity 19 | MFA | Wk-41 | 1 | Wk-42 |  | X | X | X |  | Not Started
Activity 20 | Mining Analysis | Wk-41 | 1 | Wk-42 | X |  | X |  | X | Not Started
Delivery D3 Part 2 |  |  |  | Wk-44 (30/10/2023)
Activity 21 | Attach the Documentation | Wk-42 | 1 | Wk-43 |  | X |  |  |  | Not Started
Activity 22 | Hierarchical Clustering | Wk-42 | 1 | Wk-43 |  |  | X | X |  | Not Started
Activity 23 | Profiling | Wk-42 | 1 | Wk-43 |  |  |  | X | X | Not Started
Activity 24 | Decision tree | Wk-43 | 1 | Wk-44 | X |  | X |  | X | Not Started
Activity 25 | Discriminant Analysis | Wk-43 | 1 | Wk-44 | X | X | X |  |  | Not Started
Activity 26 | Discussion & Conclusion | Wk-43 | 1 | Wk-44 | X | X |  |  | X | Not Started
Activity 27 | Gantt update | Wk-43 | 1 | Wk-44 |  |  | X | X |  | Not Started
Delivery D4 |  |  |  | Wk-03 (15/01/2024)
Activity 1 | Cover of the work | Wk-45 | 1 | Wk-46 |  |  | X | X |  | Not Started
Activity 2 | Index | Wk-45 | 1 | Wk-46 |  |  | X | X |  | Not Started
Activity 3 | Motivation of work | Wk-45 | 1 | Wk-46 |  |  | X | X |  | Not Started
Activity 4 | Data sources | Wk-45 | 1 | Wk-46 |  | X |  |  | X | Not Started
Activity 5 | Formal description of Data structure and metadata | Wk-45 | 1 | Wk-46 |  | X |  | X |  | Not Started
Activity 6 | Explanation of data preprocessing and preparation | Wk-45 | 1 | Wk-46 | X |  |  | X |  | Not Started
Activity 7 | Statistical Description | Wk-45 | 1 | Wk-46 | X |  | X |  |  | Not Started
Activity 8 | Descriptive Analysis | Wk-45 | 1 | Wk-46 | X |  |  | X |  | Not Started
Activity 9 | Explanation of predictive models | Wk-47 | 3 | Wk-50 |  | X |  |  | X | Not Started
Activity 10 | Explanation of the clustering process and dendrograms | Wk-47 | 3 | Wk-50 | X |  |  | X | X | Not Started
Activity 11 | Descriptions of class interpretation | Wk-47 | 3 | Wk-50 | X | X |  |  |  | Not Started
Activity 12 | CPG, profiling graphs or numerical information | Wk-51 | 3 | Wk-02 |  | X | X |  |  | Not Started
Activity 13 | Final Class Profiling | Wk-51 | 3 | Wk-02 |  |  | X | X |  | Not Started
Activity 14 | Slide of PCA | Wk-51 | 3 | Wk-02 |  | X | X | X |  | Not Started
Activity 15 | Methods description | Wk-51 | 3 | Wk-02 |  |  | X | X |  | Not Started
Activity 16 | Working plan | Wk-51 | 3 | Wk-02 | X | X |  |  |  | Not Started
Activity 17 | R Script | Wk-51 | 3 | Wk-02 |  | X |  |  | X | Not Started
Presentation |  |  |  | Wk-03 (16/01/2024)
Activity 1 | Submit the Documentation | Wk-02 | 1 | Wk-02 | X | X | X | X | X | Not Started
Activity 2 | Making project Presentation | Wk-51 | 2 | Wk-01 | X | X | X | X | X | Not Started
Activity 3 | Practice oral presentation | Wk-01 | 1 | Wk-02 | X | X | X | X | X | Not Started

## Contingency Plan
Risk | How to Prevent | How to Manage
Team member leave | Communication. If someone is going to leave and the other members are aware of it the risk to the project is less | Readjustment of task distributions
Data Source untrustable | Ensure that the source of the database is trustable before making any further analysis | Be transparent at the report: write about what is known about the source and outline the reasons why it is not trustable
Work progress is lost | Each member will have at least one backup of all the project | Start again from a previous version
Inconsistency of versions in scripts | Use a version control platform like GitHub or a base script, where all the members start their work | Merge scripts
Communication lost with one member | We will have at least two ways to contact each of the members, like Gmail and WhatsApp | Contact the person from an alternative way
A team member is overworked | Have a good task distribution according to the workload of the semester | Readjustment of task distributions
Difficulties when applying a method (e.g., PCA) | Communication during all work giving tips and help when needed | Collaboration in the team. Other members can work in an activity initially planned for one if required
Imputation is done incorrectly (e.g., distributions before and after clearly differ) | The imputation is done by different methods and by different people | Repeat the imputation by another method, if possible, or leave missing values
Difficulties to explain any relation with the initial target variable in mining analysis (e.g., we do not manage to predict sales in the next 6 months) | Bibliography research or use of more advance mining techniques | Be transparent in the report
One member cannot attend the final presentation of the project | Members will know all the presentation | The explanation of the missing member is divided into the other members
Difficulties to explain the initial target variable in mining analysis (eg: we do not manage to predict sales in the next 6 months) | Perform several analysis | Be transparent in the report
One member cannot attend the final presentation of the project | Members will know all the presentation | The explanation of the missing member is divided into the other members